## Project Time Lines
GRASSROOTS START UP AND DEVELOPMENT GRANT PROJECT ACTIVITIES AND TIMELINES
1 | Prelaunch Activities and Timelines | Proposed Dates
Milestones
| Project Plan for the grant created | 30th April
| Communications drafted to publicise the grant | 14th May
| Fund webpage created and promotion scheduled | 15th May
| Promotion included in the BVSC June Bulletin | 26th May
| Online Application Process Created | 15th May
| Assessment Framwork Created | 30th May
| Due Diligence Checklist Created | 30th May
2 | Grassroots Start Up Grant Launch Round 1
| Milestone | Proposed Date
| Fund launch | 2nd Week of June 2026
| Applications open | 15th June 2026
| Drop in Session (1 week after opening) | 23rd June 2026
| Applications close | 27th July 2026
| Panelists Selected | By 16th July 2026
| Applications Downloaded and summarised | 31st July 2026
| Documents sent to Panelists | By 6th August 2026
| 1st Panel Assessment | 28th July 2026
| 2nd Panel Assessment | 19th August 2026
| Decisions communicated | 7th September 2026
| Funds Disbursed | 25th August 2026
2.2 | Post Grassroots Start Up Grant Launch Activities and Timelines
| Milestone | Proposed Date
| Communication to succesful Applicants | 7th September 2026
| Communication to Unsuccesful Applicants | 25th September 2026
| Monitoring and Evaluation | Week starting 29th September 2026-Close 30th October 2026 | 1 Month
4 | Capacity Building Training Activities and Timelines
| Training applications open | 1st week August 2026
| Training Delivered | From second week September to End of September 2026
| Format-Hybrid/Face to Face and Online-Online links created and shared and venues booked | By 2nd Week August 2026
| Support Offered -Travel/Childcare/Accessibility (budegts and planning/risk assessments done and in place) | By 3rd Week August 2026
5 | Grassroots Development Grant Launch Round 1
| Milestone | Proposed Date
| Applications open | 6th October 2026 | 6 weeks between open and close
| Applications close | 17th November 2026
| Assessment | 15th December 2026 | 4 weeks after applications close
| Decisions communicated | 22nd January 2026 | taken into account xmas holidays
| Funds disbursed | 12th Feb 2026 | 3 weeks after decision
Grassroots Development Grant Launch Round 2
| Milestone | Proposed Date
| Applications open | 25th Jan 2027 | 6 weeks between open and close
| Applications close | 8th March 2027
| Assessment | 29th March 2027
| Decisions communicated | 10th April 2027
| Funds disbursed | 12th Feb 2027

## Budgets
S/N | Item | Amount £ | Details
1 | Example: Website Hosting costs | 20 | Example :£20 per year to host website
2
3
4
5
| Total Amount Requested | 20 |  | Not to Exceed £500